## Participation
Day | Shift | Time | Activity | Duration | Responsable | Support 1 | Support 2
Tuesday | Morning | 7:30 | Load Equipments CARISSMA | 2:00 | Maikol | Paulo
|  | 9:30 | Set/Measure postion of all Targets/Sprinkles/Sensor setup | 3:00
|  | 12:30 | Lunch brake / Return Sprinter | 1:00
| Afternoon | 13:30 | Extrinsic Calibration | 3:00 | Yuri | Leticia | Maikol | Yuri Arrives 12:00 for the calibration
|  | 16:30 | Conduct Test Dry Day | 3:30 |  |  |  | Calibration and conduction of the tests can be changed to enable to collect data with sun high
| Night | 20:00 | Conduct Test Dry Night | 2:00 |  |  | Balaji
|  | 22:00 | Store Targets and Sensors | 0:30
Wednesday | Morning | 7:30 | Mount Rain Facility 10 mm/h | 2:00 | Maikol | Leticia
|  | 9:30 | Validate Rain 10 mm/h | 3:00 |  |  |  | Maikol has Meeting IPG 12:00
|  | 12:30 | Lunch Brake | 1:00
| Afternoon | 13:30 | Data Collection 10mm/h Day | 5:00 | Yuri | Maikol | Leticia
|  | 18:30 | Pause | 1:30 | Yuri | Balaji | Lukas
| Night | 20:00 | Data Collection 10mm/h Night | 2:00
|  | 22:00 | Store Targets and Sensors | 0:30
Thursday | Morning | 7:30 | Mount Rain Facility 25 mm/h | 1:30 | Maikol | Georg
|  | 9:00 | Validate Rain 25 mm/h | 2:00
|  | 11:00 | Mount Rain Facility 50 mm/h | 0:30
|  | 11:30 | Validate Rain 50 mm/h | 1:30
| Afternoon | 13:00 | Data Collection Rain 50 mm/h | 1:00 | Yuri | Leticia | Maikol
|  | 14:00 | Mount Rain Facility 25 mm/h | 0:30
|  | 14:30 | Data Collection 25 mm/h - Extrinsic Calibration | 4:00
| Night | 18:30 | Pause | 1:30 |  |  | Balaji
|  | 20:00 | Data Collection 25 mm/h Night | 2:00
|  | 22:00 | Store Targets and Sensors | 0:30
Friday | Morning | 8:00 | Intrinsic Calibration Student Project | 4:00 | Maikol | Lukas | Sayed | Ramez
| Afternoon | 12:00 | Data collection 25mm/h / Buffer | 5:00 | Yuri | Leticia | Balaji
|  | 17:00 | Pause | 1:00
|  | 18:00 | Mount Rain Facility 50 mm/h | 1:00 |  |  | Maikol
| Night | 19:00 | Pause/Buffer | 1:00
|  | 20:00 | Data collection 50 mm/h Night | 1:00
|  | 21:00 | Load Equipments back to CARISSMA | 1:30

## Tests catalog
Test | Description | Sprinkles | Target | Distance | Angle | Time | Lux at moment | Test | Description | Sprinkles | Target | Distance | Angle | Time | Lux | Test | Description | Sprinkles | Target | Distance | Angle | Time | Lux | Test | Description | Sprinkles | Target | Distance | Angle | Time
1.1 | Dry Day | Position 1 | Pedestrian | 28 | 0° | 10 | 4700 | 3.1 | Dry Day | Position 1 | Pedestrian | 28 | 0° | 10 |  | 5.1 | 25 mm/h | Position 2 | Pedestrian | 28 | 0° | 10 | 7280 | 7.1 | 50 mm/h | Position 3 | Pedestrian | 28 | 0° | 10
1.2 |  |  |  | 28 | 45° | 2 | 4250 | 3.2 |  |  |  | 28 | 45° | 2 |  | 5.2 |  |  |  | 28 | 45° | 2 | 7740 | 7.2 |  |  |  | 28 | 45° | 2
1.3 |  |  |  | 28 | 90° | 2 | 4170 | 3.3 |  |  |  | 28 | 90° | 2 |  | 5.3 |  |  |  | 28 | 90° | 2 | 7830 | 7.3 |  |  |  | 28 | 90° | 2
1.4 |  |  |  | 56 | 0° | 2 | 4090 | 3.4 |  |  |  | 56 | 0° | 2 |  | 5.4 |  |  |  | 56 | 0° | 2 | 7130 | 7.4 |  |  | Bicycle | 28 | 0° | 10
1.5 |  |  |  | 56 | 45° | 2 | 3880 | 3.5 |  |  |  | 56 | 45° | 2 |  | 5.5 |  |  |  | 56 | 45° | 2 | 5090 | 7.5 |  |  |  | 28 | 45° | 2
1.6 |  |  |  | 56 | 90° | 2 | 3920 | 3.6 |  |  |  | 56 | 90° | 2 |  | 5.6 |  |  |  | 56 | 90° | 2 | 4120 | 7.6 |  |  |  | 28 | 90° | 2
1.7 |  |  |  | 84 | 0° | 2 | 3650 | 3.7 |  |  |  | 84 | 0° | 2 |  | 5.7 |  |  | Bicycle | 28 | 0° | 10 | 7930 | 7.7 |  |  | Car | 28 | 0° | 10
1.8 |  |  |  | 84 | 45° | 2 | 3720 | 3.8 |  |  |  | 84 | 45° | 2 |  | 5.8 |  |  |  | 28 | 45° | 2 | 7810 | 7.8 |  |  |  | 28 | 45° | 2
1.9 |  |  |  | 84 | 90° | 2 | 3659 | 3.9 |  |  |  | 84 | 90° | 2 |  | 5.9 |  |  |  | 28 | 90° | 2 | 7720 | 7.9 |  |  |  | 28 | 90° | 2
1.10 |  |  |  | 112 | 0° | 2 | 3480 | 3.10 |  |  |  | 112 | 0° | 2 |  | 5.10 |  |  |  | 56 | 0° | 2 | 6540 | 7.10 |  |  | Corner Reflector | 28 | 0° | 10
1.11 |  |  |  | 112 | 45° | 2 | 3410 | 3.11 |  |  |  | 112 | 45° | 2 |  | 5.11 |  |  |  | 56 | 45° | 2 | 5810 | 7.11 |  |  | Lidar Targets | 28 | 0° | 10
1.12 |  |  |  | 112 | 90° | 2 | 3951 | 3.12 |  |  |  | 112 | 90° | 2 |  | 5.12 |  |  |  | 56 | 90° | 2 | 5690 | 7.12 |  |  | Camera Targets | 28 | 0° | 10
1.13 |  |  | Bicycle | 28 | 0° | 10 | 3370 | 3.13 |  |  | Bicycle | 28 | 0° | 10 |  | 5.13 |  |  | Car | 28 | 0° | 10 | 7510 | 8.1 | 50 mm/h Night | Position 3 | Pedestrian | 28 | 0° | 10
1.14 |  |  |  | 28 | 45° | 2 | 1603 | 3.14 |  |  |  | 28 | 45° | 2 |  | 5.14 |  |  |  | 28 | 45° | 2 | 7540 | 8.2 |  |  | Bycicle | 28 | 0° | 10
1.15 |  |  |  | 28 | 90° | 2 | 1730 | 3.15 |  |  |  | 28 | 90° | 2 |  | 5.15 |  |  |  | 28 | 90° | 2 | 7820 | 8.3 |  |  | Car | 28 | 0° | 10
1.16 |  |  |  | 56 | 0° | 2 | 2230 | 3.16 |  |  |  | 56 | 0° | 2 |  | 5.16 |  |  |  | 56 | 0° | 2 | 6070 | 8.4 |  |  | Corner Reflector | 28 | 0° | 10
1.17 |  |  |  | 56 | 45° | 2 | 4150 | 3.17 |  |  |  | 56 | 45° | 2 |  | 5.17 |  |  |  | 56 | 45° | 2 | 6500 | 8.5 |  |  | Lidar Targets | 28 | 0° | 10
1.18 |  |  |  | 56 | 90° | 2 | 3579 | 3.18 |  |  |  | 56 | 90° | 2 |  | 5.18 |  |  |  | 56 | 90° | 2 | 7160 | 8.6 |  |  | Camera Targets | 28 | 0° | 10
1.19 |  |  |  | 84 | 0° | 2 | 3590 | 3.19 |  |  |  | 84 | 0° | 2 |  | 5.19 |  |  | Corner Reflector | 28 | 0° | 10 | 6580
1.20 |  |  |  | 84 | 45° | 2 | 3040 | 3.20 |  |  |  | 84 | 45° | 2 |  | 5.20 |  |  |  | 56 | 0° | 2 | 6190
1.21 |  |  |  | 84 | 90° | 2 | 4100 | 3.21 |  |  |  | 84 | 90° | 2 |  | 5.21 |  |  | Lidar Targets | 28 | 0° | 10 | 4480
1.22 |  |  |  | 112 | 0° | 2 | 1616 | 3.22 |  |  |  | 112 | 0° | 2 |  | 5.22 |  |  |  | 56 | 0° | 2 | 5640
1.23 |  |  |  | 112 | 45° | 2 | 1632 | 3.23 |  |  |  | 112 | 45° | 2 |  | 5.23 |  |  | Camera Targets | 28 | 0° | 10 | 6240
1.24 |  |  |  | 112 | 90° | 2 | 1600 | 3.24 |  |  |  | 112 | 90° | 2 |  | 5.24 |  |  |  | 56 | 0° | 2 | 5940
1.25 |  |  | Car | 28 | 0° | 10 | 1048 | 3.25 |  |  | Car | 28 | 0° | 10 | 3600 | 6.1 | 25 mm/h Night | Position 2 | Pedestrian | 28 | 0° | 10
1.26 |  |  |  | 28 | 45° | 2 | 1000 | 3.26 |  |  |  | 28 | 45° | 2 | 3880 | 6.2 |  |  |  | 56 | 0° | 2
1.27 |  |  |  | 28 | 90° | 2 | 1600 | 3.27 |  |  |  | 28 | 90° | 2 | 3010 | 6.3 |  |  | Bycicle | 28 | 0° | 10
1.28 |  |  |  | 56 | 0° | 2 | 569 | 3.28 |  |  |  | 56 | 0° | 2 | 3220 | 6.4 |  |  |  | 56 | 0° | 2
1.29 |  |  |  | 56 | 45° | 2 |  | 3.29 |  |  |  | 56 | 45° | 2 | 3340 | 6.5 |  |  | Car | 28 | 0° | 10
1.30 |  |  |  | 56 | 90° | 2 | 262 | 3.30 |  |  |  | 56 | 90° | 2 | 3820 | 6.6 |  |  |  | 56 | 0° | 2
1.31 |  |  |  | 84 | 0° | 2 | 232 | 3.31 |  |  |  | 84 | 0° | 2 | 1712 | 6.7 |  |  | Corner Reflector | 28 | 0° | 10
1.32 |  |  |  | 84 | 45° | 2 |  | 3.32 |  |  |  | 84 | 45° | 2 | 1522 | 6.8 |  |  |  | 56 | 0° | 2
1.33 |  |  |  | 84 | 90° | 2 |  | 3.33 |  |  |  | 84 | 90° | 2 | 3010 | 6.9 |  |  | Lidar Targets | 28 | 0° | 10
1.34 |  |  |  | 112 | 0° | 2 |  | 3.34 |  |  |  | 112 | 0° | 2 | 3340 | 6.10 |  |  |  | 56 | 0° | 2
1.35 |  |  |  | 112 | 45° | 2 |  | 3.35 |  |  |  | 112 | 45° | 2 | 3140 | 6.11 |  |  | Camera Targets | 28 | 0° | 10
1.36 |  |  |  | 112 | 90° | 2 | 743 | 3.36 |  |  |  | 112 | 90° | 2 | 3120 | 6.12 |  |  |  | 56 | 0° | 2
1.37 |  |  | Corner Reflector | 112 | 0° | 10 |  | 3.37 |  |  | Corner Reflector | 112 | 0° | 10 | 2350
1.38 |  |  |  | 56 | 0° | 2 |  | 3.38 |  |  |  | 56 | 0° | 2
1.39 |  |  |  | 84 | 0° | 2 |  | 3.39 |  |  |  | 84 | 0° | 2
1.40 |  |  |  | 112 | 0° | 2 |  | 3.40 |  |  |  | 112 | 0° | 2
1.41 |  |  | Lidar Targets | 28 | 0° | 10 | 88000 | 3.41 |  |  | Lidar Targets | 28 | 0° | 10
1.42 |  |  |  | 56 | 0° | 2 | 80000 | 3.42 |  |  |  | 56 | 0° | 2
1.43 |  |  |  | 84 | 0° | 2 | 90000 | 3.43 |  |  |  | 84 | 0° | 2
1.44 |  |  |  | 112 | 0° | 2 |  | 3.44 |  |  |  | 112 | 0° | 2
1.41 |  |  | Camera Targets | 28 | 0° | 10 | 96000 | 3.45 |  |  | Camera Targets | 28 | 0° | 10
1.42 |  |  |  | 56 | 0° | 2 | 95000 | 3.46 |  |  |  | 56 | 0° | 2
1.43 |  |  |  | 84 | 0° | 2 |  | 3.47 |  |  |  | 84 | 0° | 2
1.44 |  |  |  | 112 | 0° | 2 |  | 3.48 |  |  |  | 112 | 0° | 2
2.1 | Dry Night | Position 1 | Pedestrian | 28 | 0° | 10 |  | 4.1 | Dry Night | Position 1 | Pedestrian | 28 | 0° | 10
2.2 |  |  |  | 56 | 0° | 2 |  | 4.2 |  |  |  | 56 | 0° | 2
2.3 |  |  |  | 84 | 0° | 2 |  | 4.3 |  |  |  | 84 | 0° | 2
2.4 |  |  |  | 112 | 0° | 2 |  | 4.4 |  |  |  | 112 | 0° | 2
2.5 |  |  | Bycicle | 28 | 0° | 10 |  | 4.5 |  |  | Bycicle | 28 | 0° | 10
2.6 |  |  |  | 56 | 0° | 2 |  | 4.6 |  |  |  | 56 | 0° | 2
2.7 |  |  |  | 84 | 0° | 2 |  | 4.7 |  |  |  | 84 | 0° | 2
2.8 |  |  |  | 112 | 0° | 2 |  | 4.8 |  |  |  | 112 | 0° | 2
2.9 |  |  | Car | 28 | 0° | 10 |  | 4.9 |  |  | Car | 28 | 0° | 10
2.10 |  |  |  | 56 | 0° | 2 |  | 4.10 |  |  |  | 56 | 0° | 2
2.11 |  |  |  | 84 | 0° | 2 |  | 4.11 |  |  |  | 84 | 0° | 2
2.12 |  |  |  | 112 | 0° | 2 |  | 4.12 |  |  |  | 112 | 0° | 2
2.13 |  |  | Corner Reflector | 28 | 0° | 10 | 2.9 | 4.13 |  |  | Corner Reflector | 28 | 0° | 10
2.14 |  |  |  | 56 | 0° | 2 |  | 4.14 |  |  |  | 56 | 0° | 2
2.15 |  |  |  | 84 | 0° | 2 |  | 4.15 |  |  |  | 84 | 0° | 2
2.16 |  |  |  | 112 | 0° | 2 |  | 4.16 |  |  |  | 112 | 0° | 2
2.17 |  |  | Lidar Targets | 28 | 0° | 10 |  | 4.17 |  |  | Lidar Targets | 28 | 0° | 10
2.18 |  |  |  | 56 | 0° | 2 |  | 4.18 |  |  |  | 56 | 0° | 2
2.19 |  |  |  | 84 | 0° | 2 |  | 4.19 |  |  |  | 84 | 0° | 2
2.20 |  |  |  | 112 | 0° | 2 |  | 4.20 |  |  |  | 112 | 0° | 2
2.21 |  |  | Camera Targets | 28 | 0° | 10 |  | 4.21 |  |  | Camera Targets | 28 | 0° | 10
2.22 |  |  |  | 56 | 0° | 2 |  | 4.22 |  |  |  | 56 | 0° | 2
2.23 |  |  |  | 84 | 0° | 2 |  | 4.23 |  |  |  | 84 | 0° | 2
2.24 |  |  |  | 112 | 0° | 2 |  | 4.24 |  |  |  | 112 | 0° | 2

## Rain measurement
Monting positions
Object | Position x | Position y | RTK Lat | RTK Long
Sensor | 0 | 0 | -32.45 | -35.62
Sprinkle 1 | 5.5 | 4 | -38.82 | -38.08
Sprinkle 2 | 5.5 | -4 | -32.05 | -42.42
Sprinkle 3 | 21.5 | 4 | -47.44 | -51.52
Sprinkle 4 | 21.5 | -4 | -40.73 | -55.86
Sprinkle 5 | 37.5 | 4 | -56.14 | -64.94
Sprinkle 6 | 37.5 | -4 | -49.4 | -69.3
Sprinkle 7 | 53.5 | 4 | -64.81 | -78.4
Sprinkle 8 | 53.5 | -4 | -58.08 | -82.77
Sprinkle 9 | 69.5 | 4 | -73.4 | -91.87
Sprinkle 10 | 69.5 | -4 | -66.79 | -96.21
Sprinkle 11 | 85.5 | 4 | -82.14 | -105.3
Sprinkle 12 | 85.5 | -4 | -75.45 | -109.66
Sprinkle 13 | 101.5 | 4 | -90.73 | -118.68
Sprinkle 14 | 101.5 | -4 | -84.17 | -123.07
Sprinkle 15 | 117.5 | 4 | -99.53 | -132.17
Sprinkle 16 | 117.5 | -4 | -92.43 | -136.33
Target 1 | 28 | 0 | -47.62 | -59.17
Target 2 | 56 | 0 | -62.82 | -82.74
Target 3 | 84 | 0 | -77.9 | -106.15
Target 4 | 112 | 0 | -93.18 | -129.74